## Instructions
Job shop schedule template
A Monday–Friday production schedule for a small job shop or machine shop. It adds up the hours you typed, compares them with the hours each machine has, and flags work scheduled after its due date. It does not choose a sequence or move a job when you insert another one.
What each sheet is for | Instructions — this page. Jobs — one row per routing step: job number, customer, part, quantity, due date, priority, operation, machine, hours, and the date you plan to run it. Machines — machine name, hours per day, and days per week. Weekly capacity is hours per day times days per week. Schedule — those hours placed on the Monday–Friday of the week in C3, next to each machine's capacity.
Set up | 1. On Machines, replace the sample machines with yours. Hours per day is time the machine can run, not the shift posted on the wall. Breaks the machine is down for belong in the number you type. 2. On Schedule, set C3 to the Monday of the week you are planning. If it is not a Monday, the cell beside it says so. The five columns follow that date. 3. On Jobs, enter one row per routing step. Repeat the job number, customer, part, quantity, and due date. Number the operations in the order the part travels. 4. Put setup and run together in Hours. If a step spans two days, use two rows and two dates. 5. Read Schedule. A red day is over that machine's hours per day. Days over counts those days. Hours over week is only the weekly total. 6. Delete rows marked Sample, or type over them and clear the Sample cell, before you use the totals.
Colors and words | Red day on Schedule — that day's hours are over the machine's hours per day. Late — the scheduled date is after the due date. On time — the step is scheduled on or before the due date. Unscheduled — the job number is filled in, but the due date or the scheduled date is blank. Those hours are not on the week. Not on Machines sheet — the machine name does not match column A on Machines, so the hours will not appear on the week. Rush, High, Normal — labels for you and for the filter. The sheet does not sort or reserve capacity by them. Yellow cells are inputs. Gray cells are formulas. If you type over a gray cell, copy the formula back down from the row above.
Rush jobs and two jobs on one machine | Add a row for each routing step of the rush job and set Priority to Rush. Put the scheduled date on the day you hope to run it. If that day turns red, the machine does not have the hours. Move a different job by changing its scheduled date, or split the rush step across two dates with two rows. Read Timing on every step you moved. Late means the new date misses the due date. You decide whether the promise changes or a different job moves. The workbook will not pick a winner. Two jobs on the same machine on the same date are added together. That sum is the conflict.
Worked example (sample week of 2026-03-16) | With the sample rows still in the file: Haas VF-2 on 2026-03-18 is 9.5 hours against 8; Weld cell on 2026-03-16 is 10.0 hours against 8. Late: job 1710 op 3. Unscheduled: job 1944 op 1. Rush operations dated this week: 6. Machines over their weekly hours: 0. A week can be inside its weekly hours while a single day is red.
What this file will not do | It will not sequence a routing, level the load, or push other jobs later when you insert one. It checks the hours and dates you typed. It covers Monday through Friday for one week. Saturday work has to be noted on the job or folded into Friday. A second shift is a higher hours-per-day number, not an automatic calendar. If several people edit the week at once, or the file only works because one person remembers which cells not to touch, a single spreadsheet is usually the wrong place to keep doing that. Add more job or machine rows by copying the last row so the formulas come with it. Do not insert a row above the header.
Source | Free to use and edit. The sample jobs, customers, and machine names are made up so the colors are visible before you delete them. exactapps.dev/job-shop-schedule-template

## Jobs
Jobs and routing
One row per routing step. Repeat the job number on every step. Machine names must match the Machines sheet (spaces matter; capitalization does not). Yellow cells are where you type. Gray cells are formulas.
SAMPLE DATA — rows marked Sample are fictional. Delete them, or type over them and clear the Sample cell, before you trust the totals.
Job # | Customer | Part | Qty | Due date | Priority | Op # | Operation | Machine | On machine list | Hours (setup + run) | Scheduled date | Timing | Job total hours | Sample data
1842 | Northline | Bracket | 24 | 2026-03-20 | Normal | 1 | Saw blanks | Saw |  | 2 | 2026-03-16 |  |  | Sample
1842 | Northline | Bracket | 24 | 2026-03-20 | Normal | 2 | Mill | Haas VF-2 |  | 6.5 | 2026-03-16 |  |  | Sample
1842 | Northline | Bracket | 24 | 2026-03-20 | Normal | 3 | Mill finish | Haas VF-2 |  | 4 | 2026-03-17 |  |  | Sample
1766 | Harbor Castings | Housing | 12 | 2026-03-20 | Normal | 1 | Mill | Haas VF-2 |  | 5 | 2026-03-19 |  |  | Sample
1766 | Harbor Castings | Housing | 12 | 2026-03-20 | Normal | 2 | Mill finish | Haas VF-2 |  | 3.5 | 2026-03-20 |  |  | Sample
1888 | Apex Drives | Shaft | 30 | 2026-03-19 | High | 1 | Setup and turn | Mazak QT-250 |  | 2 | 2026-03-16 |  |  | Sample
1888 | Apex Drives | Shaft | 30 | 2026-03-19 | High | 2 | Turn | Mazak QT-250 |  | 7.5 | 2026-03-17 |  |  | Sample
1888 | Apex Drives | Shaft | 30 | 2026-03-19 | High | 3 | Turn | Mazak QT-250 |  | 7.5 | 2026-03-18 |  |  | Sample
1888 | Apex Drives | Shaft | 30 | 2026-03-19 | High | 4 | Finish turn | Mazak QT-250 |  | 4 | 2026-03-19 |  |  | Sample
1710 | Ridge Fab | Frame | 8 | 2026-03-17 | High | 1 | Weld | Weld cell |  | 6 | 2026-03-16 |  |  | Sample
1710 | Ridge Fab | Frame | 8 | 2026-03-17 | High | 2 | Weld | Weld cell |  | 6 | 2026-03-17 |  |  | Sample
1710 | Ridge Fab | Frame | 8 | 2026-03-17 | High | 3 | Weld | Weld cell |  | 4 | 2026-03-18 |  |  | Sample
1901 | Keystone | Cover | 6 | 2026-03-20 | Rush | 1 | Saw blanks | Saw |  | 1.5 | 2026-03-18 |  |  | Sample
1901 | Keystone | Cover | 6 | 2026-03-20 | Rush | 2 | Mill | Haas VF-2 |  | 7 | 2026-03-18 |  |  | Sample
1901 | Keystone | Cover | 6 | 2026-03-20 | Rush | 3 | Weld | Weld cell |  | 5 | 2026-03-19 |  |  | Sample
1901 | Keystone | Cover | 6 | 2026-03-20 | Rush | 4 | Inspect | Inspection |  | 1 | 2026-03-20 |  |  | Sample
1922 | Sample Stampings | Plate | 15 | 2026-03-20 | Normal | 1 | Weld | Weld cell |  | 4 | 2026-03-16 |  |  | Sample
1922 | Sample Stampings | Plate | 15 | 2026-03-20 | Normal | 2 | Inspect | Inspection |  | 1.5 | 2026-03-19 |  |  | Sample
1930 | Inland Tool | Fixture | 4 | 2026-03-18 | Rush | 1 | Mill | Haas VF-2 |  | 2.5 | 2026-03-18 |  |  | Sample
1930 | Inland Tool | Fixture | 4 | 2026-03-18 | Rush | 2 | Inspect | Inspection |  | 0.5 | 2026-03-18 |  |  | Sample
1944 | Demo Hydraulics | Manifold | 10 | 2026-03-20 | Normal | 1 | Mill | Haas VF-2 |  | 3 |  |  |  | Sample

## Machines
Machines and capacity
Hours per day is the time that machine can actually run, not the length of the shift on the wall. A second shift is a larger hours-per-day number (16 for two 8-hour shifts), not a second row, unless it really is a second machine. Days per week is how many of those days you run. This workbook's grid is Monday–Friday, so 5 is the usual value.
SAMPLE DATA — replace these machines with yours. Keep each name unique. Empty rows below are for more machines.
Machine | Hours per day | Days per week | Weekly capacity (h) | Notes | Sample data
Haas VF-2 | 8 | 5 |  | Vertical mill, one shift | Sample
Mazak QT-250 | 8 | 5 |  | CNC lathe, one shift | Sample
Weld cell | 8 | 5 |  | One welder, one shift | Sample
Saw | 6 | 5 |  | Horizontal bandsaw, shared | Sample
Inspection | 4 | 5 |  | Bench, not a full shift | Sample

## Schedule
Weekly schedule
Set the Monday in C3. Each day cell adds Hours from Jobs where the machine matches and the scheduled date matches. A red day is over that machine's hours per day. The sheet does not move jobs for you.
Week start (Monday) | 2026-03-16
Machine |  | Week load (h) | Hours / day | Week capacity (h) | Hours over week | Days over
This week
Late operations
Unscheduled operations
Rush operations dated this week
Machines with a day over capacity
Machines over their weekly hours
How to read a red day
The hours on that date are higher than Hours/day for that machine. Every job on that machine that day is added together. Change a scheduled date on Jobs, or split one operation into two rows with two dates. Priority does not change the math. A rush hour counts the same as any other hour.
Late vs unscheduled
Late means the scheduled date is after the due date. The due date itself is on time. Unscheduled means the job number is filled in but the due date or the scheduled date is blank. Blank dates are left off this grid.
Missing hours
If On machine list says Not on Machines sheet, those hours are not here. Spelling and spaces have to match. Capitalization does not.
Sample week to check the file
With the sample rows still in the file: Haas VF-2 on 2026-03-18 is 9.5 hours against 8; Weld cell on 2026-03-16 is 10.0 hours against 8. Late: job 1710 op 3. Unscheduled: job 1944 op 1. Rush operations dated this week: 6. Machines over their weekly hours: 0. A week can be inside its weekly hours while a single day is red.
Note on C3: Type the Monday of the week you are scheduling. The five day columns follow this date.